| Activity | When | Why | Who | How | Grants available |  | Priorities covered from 2010-2012 |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Developing WCN webpage as an online interactive platform | Nov 2010-March 2011 | To update the information in the webpage and re-design it to become more user-friendly for funders, potential members and media, create a contemporary visual identity for WCN, and an interactive platform to members to upload carfree news / events. | Sustainable transportation activists / organisations over the world. | Networking Grant might cover this. Then we need web programmer and visual designer to come up with a new identity. | YIA 3.1 /4.3 networking EYF CAT B (1st of October 2010) Administrative grants Private foundations |  | Support and empower local groups to influence urban planning through effective public participation |
| Partnership Building Activity : Building the Future | December 2010 | To bring the SC, MC and ICC together with network members, to have discussions about Carfree activities, future collaborations and plans. | Steering Commute, Management Commute, ICC and member organizations. | In order to apply the grand, WCN needs the agreement from organizations who agree to send participants. 70% of travel, food and stay will be covered by the grand. | YIA 3.1 (September 2010) |  | Support and empower local groups to influence urban planning through effective public participation |
| Carbusters Rising | Jan-Dec 2011 | Carbusters needs a new marketing plan, distributed widely and reach out more public | A new marketing manager, new distributors | The spread editors, contributors, wannabes, possible authors get together in Prague, creating a workshop on the new issue, graphics, distribution etc. | EYF CAT B? | Updating and eveloping the existing projects. |  |
| Mobility Justice Action meeting | 6-10 March 2011 | Meeting of Ngo leaders to discuss dissemination of potential solutions for local problems in different parts of world. Such as bicycle use in Chinese cities, traffic light timing for pedestrians etc and start-up the events as a follow-up activity. | Meeting of 25 people around inside and outside European countries focusing on sustainable transportation | 1 facilitator from WCN, 3-4 experts. | LLP 16 July to apply! YIA (just for youngster) Private funds | Support and empower local groups to influence urban planning through effective public participation |  |
| Alternatives are ON; Walking, cycling, public transport | 22-30 April 2011 | Follow up: supporting campaigns eg. on stopping the closure of local public transport lines, unwanted public transport privatisation, the closure of local services, or promoting innovative rural transport services, ‘slow travel’, making public transport easier to use than cars etc. To be done through mobility justice alerts, meetings, articles in Carbusters, media work and resources. | Host by some member organisation | Training course based in this topic | LLP 16 July to apply! YIA (just for youngster) Private funds | Bring together and empower diverse interest groups to become more active in promoting alternatives to the car. |  |
| Youth Exchange in Guadalajara, Mexico | June 2011 | Informal education on global warming and sustainable transportation issues. (to bring people from Europe to TCC X) | About 30 people over Europe; members and the WCN people | Fundraiser applies the grants; ICC needs to realise the exchange; In case there is budget, an outsider facilitator to be hired. | such as; MOTT Soros Rockefeller | Bring together and empower diverse interest groups to become more active in promoting alternatives to the car. |  |
| Training Course | 6-13 August 2011 | Informal education on global warming and sustainable transportation issues. | About 30 people over Europe; members and the WCN people |  | YIA 3.1 Visegrad EYF CAT A 1st of October | Bring together and empower diverse interest groups to become more active in promoting alternatives to the car. |  |
| World Carfree Day! | 18-24 September 2011 | Prague City has a kick since 2009 and organising bigger events each year celebrating the 22 September. WCN should have a project to help promoting the action in local level by creating a supporting activity which integrates with Auto*Mat | All members of WCN | Local actions on this day, critical mass all around the world. Materials to be distributed from the office | Administrative grants | Support local groups promoting or defending alternatives to the car. |  |
| Partnership Building Activity | 21-27 October 2011 | To bring the SC, MC and ICC together with network members, to have discussions about Carfree activities, future collaborations and plans. | Steering Commute, Management Commute, ICC and member organizations. | In order to apply the grand, WCN needs the agreement from organizations who agree to send participants. 70% of travel, food and stay will be covered by the grand. | YIA 3.1(June 2010) | Bring together and empower diverse interest groups to become more active in promoting alternatives to the car. |  |
| Picture, video exhibition | 2nd half of 2011 | To show to the people the problems that the car culture is bringing to the society | All member organisations | Along summer and during the second half of the year pictures will be taken in different places all around the world about the abuse of the car in our society and how the cities are empty of cars during summer and opportunities that these brings for the pedestrian. These pictures/videos will be sent to the office and from the office they will create a website showing that. As well will be a moving exhibition that will go from country to country to show these pictures and videos with some text about the abuse of the cars. | EYF Cat B | The economics of car use |  |
| EEB Membership | 2011 | EEB is a network of organizations which are lobbying effectible to the European governments, being part of them is a way to influence governments through our work inside of them | delegates of WCN | Applying for membership. Being involved in EEB will allow as well to all the members of the network to participate in the meetings that EEB is doing all along the year about environmental topics. | Administrative grant | Promote inclusion of external costs into transport. |  |
| Follow up of the politics decisions | 2011 | Fight against the promotion of the use of the car culture promoted by the EU | All member organizations | Follow up from the board of WCN to announce the meetings from the politicians at European level that will promote the use of the car. Distribute this information to all the members and carry out the same day local protest in all the members. These actions can be from critical mass, protests in the street, making round tables in the centers of the MO | xxx | Increase public awareness of the full personal, societal and environmental costs of car use. |  |
| Exchange |  | benefits of carfree living | 5-6 member organisations | They will share information about the benefits of carfree living using for that different techniques. As well could be the start of a working group based on this topic | LLP, YIA DG environment, EYF A | Bring together and empower diverse interest groups to become more active in promoting alternatives to the car. |  |
| Campaign | 2011 | Organise cultural programmes to promote a sustainable lifestyle without the use of the car and thanks to a better city planning | All member organizations | Organising at local level cultural events as concerts, theaters, outdoor activities… at the same time holding stands that will promote the awareness of the use of the car. | EYF cat B Private funding Administrative grants LLP Culture programme | Increase public awareness of the full personal, societal and environmental costs of car use. |  |
| Training course: empowering your organisation | 2011 | This TC will try to improve the performance of the organization and to increase the skills of the organization in the sense of management, funding and networking. | 10-12 Member Organisations and external organisations | Hosted in Prague by the office, will be applied to local level and contacted the trainers and partners for this project | YIA EYF CAT A | Support local groups promoting or defending alternatives to the car. |  |
| Summer Camp | Summer | This summer camp will have three objectives: First one to host our AGM in order to plan activities changes documents, focus in policy making and take decisions, Second one to promote the exchange of information among the NGOs participating showing the methods that they are promoting in their daily actions. Will be a chance to meet the people from WCNE for some days in order to strength contacts and networking. Third objective to have a little of fun | All member organisations | Hosted by one member of WCNE preferable from central Europe. The activities are to be define depending on the members participating. | Local funding to the government of the country applying and | Support local groups promoting or defending alternatives to the car. |  |
| TC Planning a future city | 2011 | TC with the aim to promote the benefits of a better urban planning in the cities or in the areas, as well how the people can influence on them with techniques as urban guerrilla | 10-12 Member Organisations and external organisations | Hosted by one member of WCNE preferable from central Europe. The activities will include workshops, round tables, open spaces | LLP EYF YIA DG environment | The promotion of socially inclusive alternatives to the car |  |
| workshops at local level to share and spread knowledge through examples | 2011 | To promote and give visibility to the WCN movement all around the world and motivate with the example | All member organisations | One coordinator can manage the promotional materials and ask for funding to support this event at local level. | LLP, YIA, | The promotion of socially inclusive alternatives to the car |  |
| TC Intouch | 2011 | InTouch is a training course for youth leaders to develop their competences in organising international youth exchanges, especially with the stress on intercultural learning, programme running and facilitation of a group process. It is a short, practical and experiential workshop about the basics of organising and managing international actions | 10-12 Member Organisations and external organisations | Hosted in Prague by the office, will be applied to local level and contacted the trainers and partners for this project | YIA EYF CAT A | Support local groups promoting or defending alternatives to the car. |  |